## Sheet1
General scope
General code/server setup |  | 30
Users / Roles |  | 40
Administration or private register page |  | 10
Businesses |  | 20
Design with responsiveness |  | 100
Teams |  | 30
User permissions |  | 40
Formulas and sharing |  | 60
Projects |  | 20
| Lists | 80
| Chaining and editor for this | 80
Tasks |  | 30
| Delegation | 20
| Triggerring and Scheduling | 80
| Alerts and notifications (email and SMS), settings per role per task per business | 65
Content / resources |  | 60
Clients and task groupping |  | 40
805
Iteration 1 | 06/19-07/26
General code/server setup |  | 30
Design with responsiveness | Initial drafts | 20
Formulas and sharing | Formulas base logic, no sharing | 30
Projects |  | 20
| Lists | 80
| Chaining and editor for this (base logic) | 40
Tasks |  | 30
| Delegation | 20
270
Iteration 2 | 07/26-08/26
Users / Roles |  | 40
Administration or private register page |  | 10
Businesses |  | 20
Design with responsiveness |  | 80
Formulas and sharing | Sharing | 30
Projects
| Chaining and editor for this | 40
Tasks
| Triggerring and Scheduling | 80
300
Iteration 3 | 08/19-09/10
Teams |  | 30
User permissions |  | 40
Tasks
| Alerts and notifications (email and SMS), settings per role per task per business | 65
Content / resources |  | 60
Clients and task groupping |  | 40
235